## ListOfFeatures
Product Backlog - Project Title (List of your features)
User Stories / List of features
users are able to sign up and create an account with the webpage
users are able to log in to their profile for more personal use of the website
users are able to view and edit their profile
users are able to subscribe to our newsletter

## sprint1
Sprint Backlog : Sprint 1 Feb 7 - Feb 11
BACKLOG TASK & ID | STORY POINTS (NR) | ASSIGNED TO | STATUS
Pre Sprint
Task Brainstorm about the feautures of our Portfolio |  | TOGETHER | DONE
Task: Design our Database |  | TOGETHER | DONE
Task: Set up GitHub |  | TOGETHER | DONE
Task: Universal header and footer |  | TOGETHER | DONE
Feature #1 Sign up page |  | Mehdi
Task: Create a layout for the signup page |  |  | Done
Task Design the page |  |  | Done
Taks: Design the db and table |  |  | Done
Feature #2 Log in page |  | Wafa
Task: Create a Layout for Login page |  | - | DONE
Task: Design the Page |  | - | DONE
Task: Create the table of Log in Page |  | - | DONE
-
Feature #3 Profile page |  | Anika
Decide elements for profile page (name, email, password, usename) |  |  | DONE
create and design layout for profile page |  |  | DONE
create table for profile page |  |  | DONE
Connect profile page and login page
Feature #4 Subscribe to Newsletter |  | Wafa
Task : Create layout for after login |  | - | DONE
Task design the page |  | - | DONE
Task create the db for the Newsletter subscribers |  | - | DONE
TOTAL
Hints:
During this week, you should update your exisiting pages that is your pages have universarl header and footer.
Upload this excel file to your project Repo in GitHub and update it regulaly.
You have planned your features and have distributed work among your team members
You have designed your database. Make sure that each member has his/her own table to work with.
You have create a GitHub repo and each member is added as collaborator.
Please make regular commits and get familiar with the development activities by utilizing version control.
Uploaing your files to GitHub repo is not acceptable. It will have negative impact on your grade.
Ask questions during the consultation sessions if you are not sure about how you are proceeding

## sprint2
Sprint Backlog : Sprint 2 (Feb 14 - Feb 18)
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS
Feature #2 Log in page |  | Wafa
Task: upload the db design in repo |  | - | DONE
Task: Upload the project scrum in repo |  | - | DONE
Task: Enabling gitHub pages |  | - | DONE
Task: Create login page |  | - | DONE
Feature #4 Subscribe to Newsletter |  | Wafa
Task: create afterlogin page |  | - | DONE
Task connect afterlogin with login |  | - | DONE
Task Add Javascript subscribe pop up |  | - | DONE
User Story #3
Task
Task
Task
Task
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL
Hints:
You are working on tasks that you have been assigned to in your team.
You are present in your team meetings.
You are familiary with the GitHub repo for your project work.
You are doing regular commits and you have the latest version of the website in your local device.

## sprint3
Sprint Backlog : Sprint 3 (Feb 21 - Feb 25)
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS
Log in page |  | Wafa
Task: Connect Login db with Login page |  | - | DONE
Task: Connect Log in db with Sign up table |  | - | DONE
Task: Connect Log in db with my profile table |  | - | DONE
Task: Update project scrum every 3 days |  | - | DONE
TO DO |  | Wafa
Task:Creating project db |  | - | DONE
Task: creating adb for all and connecting it to their pages |  | - | DONE
Task : Editing and uploading scrum |  | - | DONE
Task : Sharing sql file to gitHub repo |  | - | DONE
TO FINALIZE THE PROJECT |  | Wafa
Task Upload files in Shell.hamk.fi |  | - | DONE
Task Uplaod db tables to shell |  | - | DONE
Task Upload the last scrum version |  | - | DONE
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL
Hints:
You are working on tasks that you have been assigned to in your team.
You are present in your team meetings.
You are familiary with the GitHub repo for your project work.
You are doing regular commits and you have the latest version of the website in your local device.
Finalize your work and start to preare for the project review.
Make sure that your repository, shell.hamk.fi servers all have the latest version of your website.